JIRCAS-THAI Rainfed Project 
Structure (Theme, Sub-theme, Specific sub-theme)

| Theme, Sub-theme & Specific sub-theme | Year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| 1. Assessment of the regional water availability and identification of factors limiting more efficient use of water in existing farming systems | ● | ● | ● | ● | ● |  |  |
| 1-1. Assessment of regional water potentiality 1-1-1. water resource assessment 1-1-2. soil moisture assessment | 〇 〇 | 〇 〇 | 〇 〇 |  |  |  |  |
| 1-2. Identification of conditions to activate water and land resources utilization in rainfed area 1-2-1. Development of technology for water resources and land resources management in rainfed area 1-2-2. Development of techniques to estimate available water resources for small watersheds in rainfed area 1-2-3. Development of technology to prevent leakage from an irrigation pond by soil improvement | 〇 〇 〇 | 〇 〇 〇 | 〇 〇 〇 | 〇 | 〇 |  |  |
| 1-3. Identification of farm management and marketing factors limiting more efficient water use in existing farming systems 1-3-1. Clarification of the relationship between water use and farm management system 1-3-2. Clarification of marketing systems in fruits and vegetables | 〇 〇 | 〇 〇 | 〇 〇 |  |  |  |  |
| 2. Development of crop production technologies for more effective water use | ● | ● | ● | ● | ● | ● | ● |
| 2-1. Development of technologies for water collection and supply in unstable and small-scale water resources 2-1-1. Development of water collection and supply technology in unstable and small-scale water resources 2-1-2. Development of technologies for appropriate farmland use based on the conditions of the water resources.. |  |  |  | 〇 | 〇 | 〇 〇 | 〇 〇 |
| 2-2.Development of production technologies with improved water use efficiency for vegetable and fruit crops 2-2-1. Development of cultural practices to improve utilization of water stored in subsoil 2-2-2. Elucidation of water and nutrient dynamics under water-saving cultivation | 〇 〇 | 〇 〇 | 〇 〇 | 〇 〇 | 〇 〇 | 〇 〇 | 〇 |
| 2-3. Breeding and utilization of biomass forage crops resistant to water stress conditions 2-3-1. Development of high biomass forage crops tolerant to water stress by interspecific, intergeneric crossing 2-3-2. Nutritional evaluation and utilization of forage crops resistant to water stress as cattle feed 2-3-3. Improvement of feeding management practices of dairy cattle | 〇 〇 〇 | ○ 〇 〇 | ○ 〇 〇 | 〇 〇 〇 | ○ 〇 〇 |  |  |
| 3.Adaptation and integration into farming systems of new technologies through participatory methods | ● | ● | ● | ● | ● | ● | ● |
| 3-1. User needs identification and collaborative testing of technologies for water efficient, high value production systems 3-1-1. Development of technology menus through priority identification by farmers and community 3-1-2. Assessment of economic viability, environmental benefits, and acceptability through on-farm testing of technologies | 〇 〇 | 〇 〇 | 〇 〇 | 〇 〇 | 〇 | 〇 | 〇 |
| 3-2. Development of guidelines for more water efficient watershed management based on improved production systems 3-2-1. Regional mapping of conditions for wider adoption of tested systems 3-2-2. Application of tested systems into other areas (scaling up) |  |  | 〇 | 〇 | 〇 〇 | 〇 〇 | 〇 〇 |